Annual Meeting Time Line

180 Days Prior   Date: _________________

- From by-laws, any direction from previous annual meeting, and in communication with BoD set meeting date, time and location

- Reserve Meeting Space

90 Days Prior    Date: __________________

- Verify meeting Date, Time and Location with BoD

- Ensure Meeting Space is Reserved

- Determine which directors (if not all) terms are ending

- Determine is there will be a social event in conjunction with the meeting

  - Set date, time, and place for social

  - Reserve Space if Required

- Post on web page calendar

- Include date and place in newsletter

70 Days Prior    Date: _________________

- Prepare First Notice of Election, Candidate Nomination Form, Candidate Information Sheet, Owner Information Form

  - May Use Previous Year as template or use the Gray’s Systems “blue book” for example

  - Make sure date, time and place is in the notice

  - May or may not list directors positions up for election

- Ensure all dates, times, place, match up on different forms and proof read entire notice; especially if cut and paste form other files

- Include language of having Candidate Nomination form in by 40 day prior

- Include language of having a Candidate Info sheet in by 35 days prior

- HOAs can use this process but make sure you check by-laws for nomination committees and nominations from the floor

65 Days Prior    Date: _____________________

- Have 1st “Mail Out” package ready to go

60 Days prior    Date: __________________

- Due date for first notice of election

- Send via email blast from web page and post notices and other material on line

- Email current directors they must complete the candidate nomination form as well

40 Days Prior    Date: ___________________

- Collect all Candidate Nomination Forms

- Verify Eligibility

- Send Written verification of receipt and eligibility or not to candidates

- Prepare Second Notice of Election package

  - Second Notice

    - Use Prior year mail out or Grays blue book

    - Still must send even if no election is required due to equal or fewer candidates than vacancies

  - Ballot

    - Instructions can be on ballot or in second notice (prefer notice)

    - Alphabetical order

    - HOA depends on By-laws

    - Outer and inner envelopes

  - Proxy

    - General and Limited Proxy with Substitution line at the bottom

    - Use Grey’s blue book for sample

    - Make sure person listed as “generic’ proxy holder is going to attend the meeting in person. Usually Secretary or President.

    - Limited

      - Always include vote to roll over profit or loss to next year’s financials

      - If requested by board,

        - include vote to lower reserves

        - vote to waive audit

      - Other items of requiring ownership votes and such like changing declaration/by-laws, changing common property, etc.

  - Meeting Notice with Agenda

    - Use standard agenda from by-laws and add any actual votes or presentations

    - Include Organizational Meeting Notice

35 Days Prior    Date: _____________________

- Collect all candidate information sheets

- Complete Second Notice package

30 Days Prior    Date: _____________________

- Send second notice, proxy, ballot, agenda

- Plan Social Event if required

- Email blast

30 Days prior to 1 Day Prior

- Create meeting “box”/folder

- Collect ballots and proxies

  - Start list of returned items

  - Keep BoD informed of progress

- Invite special guests

15 Days Prior    Date: ___________________

- Post Membership and Organizational Meeting Notice on Property

8 Days Prior    Date: ____________________

- Finalize "Meeting Box"

  - Sign in Sheet with proxy holder names listed

  - Authorized Voter verification folder

  - Additional ballots

  - Additional ballot inner and outer envelopes

  - Ballot tally sheet

  - Additional proxies

  - Name tags

  - Markers, pens, etc.

  - Set of documents (CAM book)

  - Meeting booklets

      - Board members bound and tabbed if possible

      - Numbered pages for all

    - Cover Page

    - Notice/Agenda

    - Previous Minutes

    - Financials

      - Year-end balance sheet

      - Last period balance sheet

      - Last period income/expense statement

    - Managers report of accomplishments and current projects

    - Presentations

    - Owner List

- Visit your meeting space and make note of possible seating arrangements, check in desk placement, etc.

- Contact Board president and walk thru the meeting and responsibilities

- Finalize Social Event Plans

- Meet with “helper” to go over meeting

1 Day Prior    Date: _______________________

- Tally all proxies and ballot submissions

- Finalize meeting material, box, etc.

- If possible, set up meeting room

- Attend Social (if scheduled)

Day Of    Date: ____________________

- Arrive One Hour prior to meeting

- Complete set up

- Check In

- meet and greet with owners, do not hide

- Hold Meeting

- Attend Social (If scheduled)

Within Ten Days Post Meeting    Date: ____________________

- Complete Minutes

- Email Blast minutes and/or meeting re-cap and must include election results

- Turn in election results to office manager and accounting